## BOQ
DG-T03 Type 03 - Brick two-storey single - turnkey kit price + BOQ (Leeds / Yorkshire, ex VAT)
SUPPLY SCOPE: the Nudura ICF formwork + accessories (section A) are our FIXED price. Every other package (section B) is the turnkey-kit BOQ at indicative Leeds / Yorkshire Q4 2026 rates - supplied in good faith, every rate editable, to be checked by the relevant professional and priced by the contractor. All figures ex VAT unless stated. QUOTATION - NOT FOR CONSTRUCTION.
Install rates built from GBP/h | 34
OH&P % | 15
Contingency % | 10
VAT % | 20
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG)
Item | SKU | Qty | Unit | Order | Rate | Per | Total | Note
Nudura 6in Standard straight form (pre-cut) | NUS-I0096-06-PC | 92 | nr | 31 x 3 | 149.37 | box of 3 | 4630.47 | every form from the populated model, Nudura Bond, no stack joints
Nudura 6in Standard 90 deg corner form (pre-cut) | NUS-I0090-06-PC | 36 | nr | 6 x 6 | 154.41 | box of 6 | 926.46
End caps 152 mm (6in) - opening jambs | NUS-A0ECF-06 | 36 | nr | 1 x 40 | 105.84 | box of 40 | 105.84
Lintel closures 152 mm (6in) - heads + sills | NUS-PLINT-06 | 42 | nr | 1 x 60 | 181.44 | box of 60 | 181.44 | 3 per lintel piece
Spray foam (1 can per 22 forms) | NUS-SF-BOX | 6 | nr | 1 x 12 | 75.6 | box of 12 | 75.6
Fibre tape (1 roll per 50 forms) | NUS-FT-BOX | 3 | nr | 1 x 10 | 52.5 | box of 10 | 52.5
Protective tape | NUS-PT-BOX | 1 | nr | 1 x 4 | 33.6 | box of 4 | 33.6
Bracing + alignment hire (1 stillage x 1 wk) | ALIGN | 1 | stillage | 1 weeks | 80 | stillage | 80 | hire = the ICF install only: 2 d install + 1 pour + 1 cure + 1 strike = 5 working days -> 1 wk
BuildEase pre-cut service (setup + per form + cuts) | PRECUT | 128 | forms | 55 cut forms |  |  | 469 | GBP 350 setup + 0.50 / form + GBP 1 / m cut (standard type - modelling included)
Haulage - Tankersley S75 3DH to Leeds (<= 40 miles, 1 artic) | HAUL | 1 | load |  | 335.27 | load | 335.27
Supply total
B. TURNKEY-KIT BOQ - SUMMARY OF BILLS (each bill on its own sheet; edit the yellow cells there)
Bill 1 - Preliminaries
Bill 2 - Groundworks + substructure
Bill 3 - ICF walls (install + concrete)
Bill 4 - Roof structure + floors (carpentry: supply + install incl. fixings)
Bill 5 - Roof coverings + rainwater goods
Bill 6 - External wall finish
Bill 7 - Opening schedule (doors + windows)
Bill 8 - Electrical installation
Bill 9 - Design + approvals (provisional)
BOQ net
BOQ + OH&P
TOTAL NET (A + B)
+ contingency
TOTAL inc VAT
C. PROGRAMME (working days)
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Site setup + setting out; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 0.5; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | welfare, skip, set out the raft
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Below ground - excavation, muck away, drainage; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 2.2; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 2 operatives + excavator
| Footings / substructure - hardcore, DPM, mesh, starter bars | 1 | days
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Raft pour + power float; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 1; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | pump on site
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Raft cure before the ICF; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 3; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | minimum before standing the forms (7 days before full load)
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: ICF install - stand forms, rebar, bracing + alignment; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 2; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 3-man gang, 4.3 min / form
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: ICF pour (walls + gables); A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 1; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 4-man pour gang + pump
| ICF cure | 1 | days
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Strike the bracing + alignment; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 1; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | alignment hire = 5 working days -> 1 wk
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: First floor, stair + roof structure; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 7.4; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | joists, deck, stair, guarding, ceiling; rafters + glulam ridge, ladders
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Roof coverings + rainwater goods; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 2.6; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 2 roofers
| Doors, windows + opening tapes | 1.5 | days
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: External finish; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 7.1; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 2 operatives (slips)
A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) SKU: Electrics + test; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Qty: 1.8; A. NUDURA SUPPLY - FIXED PRICE (BuildEase / Tremco CPG) Unit: days | 1 electrician
| Snag + clean | 0.5 | days
Total

## Bill 1
DG-T03 Type 03 - Brick two-storey single - Bill 1 - Preliminaries
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
1.1 | Site setup, welfare, skip, setting out | 1 | item | 650 | 272 |  |  |  | NGR prelims 950 - site setup, welfare, skip, setting out (single garage)
1.2 | Access scaffold / towers | 27.08 | m | 38 | 0 |  |  |  | MKT independent scaffold per m perimeter, 2 storey, 8 wk, erect + strike incl.
Bill total

## Bill 2
DG-T03 Type 03 - Brick two-storey single - Bill 2 - Groundworks + substructure
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
2.1 | Excavate raft + thickened edge (reduce level 402 + edge to 500) | 12.28 | m3 | 18 | 11.9 |  |  |  | NGR dig 32/m3 split plant / labour
2.2 | Muck away (bulked x1.25) | 15.35 | m3 | 52 | 0 |  |  |  | NGR
2.3 | RWG drainage - short run to soakaway / connection | 1 | item | 420 | 340 |  |  |  | MKT RWG to soakaway / short connection
2.4 | MOT Type 1 hardcore 150, compacted | 2.3 | m3 | 48 | 17 |  |  |  | NGR MOT Type 1
2.5 | Sand blinding + 1200g DPM | 30.02 | m2 | 5.3 | 2.04 |  |  |  | NGR DPM 1.8 + sand blinding 3.5
2.6 | A393 mesh top + bottom (laps incl.) | 6 | sheet | 70 | 11.9 |  |  |  | NGR A393 4.8 x 2.4
2.7 | Starter bars T12 @ 600 into the ICF + edge bars | 0.12 | t | 1250 | 952 |  |  |  | NGR rebar + fixing 28 h/t
2.8 | C32/40 raft concrete 200 + thickened edge | 8.44 | m3 | 152 | 40.8 |  |  |  | NGR C32/40
2.9 | Concrete pump - raft pour | 1 | pour | 650 | 0 |  |  |  | NGR concrete pump per pour
2.10 | Power float finish (garage floor, fall to the door) | 27.29 | m2 | 1.5 | 2.72 |  |  |  | MKT
Bill total

## Bill 3
DG-T03 Type 03 - Brick two-storey single - Bill 3 - ICF walls (install + concrete)
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
3.1 | Stand the Nudura forms (128 forms, 4.3 min / form): set-out, bracing + alignment, rebar, end caps / lintels | 2 | gang-day | 0 | 816 |  |  |  | BOQ Builder 4.3 min per block x 3-man gang
3.2 | Pour the ICF core (walls + gables, one day), 4-man pour gang | 1 | gang-day | 0 | 1088 |  |  |  | BOQ Builder 4.3 min per block x 3-man gang
3.3 | Strike the bracing + alignment system (after 1 day cure) | 1 | gang-day | 0 | 816 |  |  |  | BOQ Builder 4.3 min per block x 3-man gang
3.4 | Wall reinforcement T12 (vertical @ 600, horizontal alternate courses) + lintel bars - supply (fixing in the install line) | 0.37 | t | 1250 | 0 |  |  |  | NGR rebar + fixing 28 h/t
3.5 | C32/40 core concrete 6in - supply (placing in the install line) | 12.96 | m3 | 152 | 0 |  |  |  | NGR C32/40 + pour 1.2 h/m3
3.6 | Concrete pump - ICF pour | 1 | pour | 650 | 0 |  |  |  | NGR concrete pump per pour
Bill total

## Bill 4
DG-T03 Type 03 - Brick two-storey single - Bill 4 - Roof structure + floors (carpentry: supply + install incl. fixings)
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
4.1 | Wall plate 47 x 150 C24 treated on the eaves walls (bedded) | 15 | m | 5.6 | 8.5 |  |  |  | NGR C24 47x150 4.25/m + straps / anchors
4.2 | Wall plate fixings - M12 anchors into the ICF core @ 1,200 + washers | 15 | nr | 3.2 | 5.1 |  |  |  | MKT M12 anchor / resin stud into the ICF core @ 1,200 + washer
4.3 | Loose C24 rafters (cut roof) | 97.39 | m | 4.6 | 6.12 |  |  |  | NGR C24 47x175
4.4 | Glulam GL24h ridge beam 100 x 440 (framer pick, engineer to confirm) | 0.34 | m3 | 1150 | 204 |  |  |  | NGR glulam GL24h
4.5 | 225 metal-web floor joists @ 400 across the 3.07 m width (18 nr incl. doubled trimming + trimmed) | 55.21 | m | 13.5 | 4.08 |  |  |  | MKT 225 metal-web joists (Posi / PS9-type, supplier designed) per m incl. delivery
4.6 | C24 ledgers on the ICF (47 x 178 side walls, 47 x 150 deck-edge on the gables) | 16.18 | m | 6.2 | 10.2 |  |  |  | MKT 47 x 178 / 150 C24 ledger on the ICF, fixed to the cast-in connectors
4.7 | Simpson ICFVL-CW + ICFLC ledger connectors, cast into the ICF @ <= 1,200 | 18 | nr | 9.8 | 5.1 |  |  |  | MKT Simpson Strong-Tie ICFVL-CW + ICFLC ICF ledger connector (cast in during the pour)
4.8 | Joist hangers + top-chord restraint clips (trimmed joists, trimmer, doubled joists) | 40 | nr | 4.2 | 5.1 |  |  |  | MKT face-fix metal-web / trimmer hanger + top-chord clips
4.9 | 22 Egger Protect P5 T&G deck, glued + screwed | 18.64 | m2 | 12.5 | 8.5 |  |  |  | MKT 22 Egger Protect P5 T&G, glued + screwed
4.10 | Quarter-turn timber stair to AD K - 15 risers x 193 / 230, 3 kite winders, 900 wide, 40.0 deg (joinery manufacturer) | 1 | nr | 1650 | 544 |  |  |  | MKT softwood quarter-turn stair with 3 kite winders, newels, handrail + balusters on the flight (joinery manufacturer, AD K)
4.11 | 900 guarding round the stair well on the first floor | 2.91 | m | 85 | 40.8 |  |  |  | MKT 900 softwood guarding round the stair well (handrail, baserail, 32 sq balusters, newel)
4.12 | Flat wall dormer over the stair head (2018 wide): framed cheeks + face, flat joists, GRP roof 2.96 m2, fibre-cement cladding 3.13 m2, code 4 lead, fixed light 562 x 600 | 1 | nr | 2400 | 1224 |  |  |  | MKT flat wall dormer ~1.7 m: TLS-framed cheeks + face, flat joists, OSB + GRP, fibre-cement cladding RAL 7016, code 4 lead, fixed light (joiner + roofer)
4.13 | Garage ceiling - 12.5 fire-rated plasterboard + skim (30 min under the room, BC to confirm) | 17.75 | m2 | 9 | 15.3 |  |  |  | MKT 12.5 fire-rated plasterboard + skim to the garage ceiling (30 min, garage under a room - BC to confirm)
4.14 | Gable ladders (barge, rails, outriggers 47 x 72) | 34.27 | m | 1.35 | 2.72 |  |  |  | TLS 25x100 binders + diagonal bracing
4.15 | Gable lateral restraint straps @ 2 m to the trusses / rafters (both gables) | 8 | nr | 4.5 | 6.8 |  |  |  | MKT galv lateral restraint strap 30 x 5 x 1000 (BS EN 845-1)
4.16 | Carpentry sundries - nails, screws, framing anchors | 1 | item | 45 | 0 |  |  |  | MKT nails, screws, framing anchors
Bill total

## Bill 5
DG-T03 Type 03 - Brick two-storey single - Bill 5 - Roof coverings + rainwater goods
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
5.1 | Breathable roofing membrane (laps incl.) | 51.2 | m2 | 1.1 | 1.02 |  |  |  | TLS breather membrane
5.2 | Treated battens 25 x 50 @ 345 gauge | 171.6 | m | 0.85 | 0.68 |  |  |  | TLS 25x50 treated
5.3 | Marley Modern smooth grey tiles (drawn: 476, +3% breakage) | 491 | nr | 1.48 | 1.19 |  |  |  | WEB Marley Modern smooth grey ex VAT; ~0.37 h/m2 roofer
5.4 | Dry ridge + half-round ridge tiles (18 drawn) | 7.8 | m | 24 | 11.9 |  |  |  | MKT dry ridge kit + half-round ridge tiles
5.5 | Dry verge units | 11.42 | m | 14 | 6.8 |  |  |  | MKT dry verge units
5.6 | uPVC fascia 22 x 225 + vented soffit | 15.6 | m | 16 | 11.9 |  |  |  | TLS uPVC fascia / soffit
5.7 | uPVC barge boards 22 x 250 | 11.42 | m | 14 | 10.2 |  |  |  | TLS uPVC barge board
5.8 | Half-round gutter 112 black + fittings | 15.6 | m | 11 | 6.8 |  |  |  | TLS half-round gutter + brackets
5.9 | Downpipe sets 68 round black: swan neck to the outlet, clipped to the side wall (6 clips), shoe | 2 | nr | 38 | 34 |  |  |  | TLS downpipe set
Bill total

## Bill 6
DG-T03 Type 03 - Brick two-storey single - Bill 6 - External wall finish
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
6.1 | Monolith BrickPlus slips 215 x 65 x 20 - supply + fix + point (flat area) | 87.66 | m2 | 42 | 37.4 |  |  |  | MKT Monolith BrickPlus-type 20 mm slips (no insulation - the Nudura EPS is the substrate)
6.2 | L-shaped corner slips (drawn: 432 legs) | 440 | nr | 1.65 | 1.02 |  |  |  | MKT L-shaped corner slips
6.3 | Slip adhesive 25 kg | 18 | bag | 19.5 | 0 |  |  |  | MKT flexible slip adhesive 25 kg (~5 kg/m2)
6.4 | Pointing mortar 25 kg | 15 | bag | 16 | 0 |  |  |  | MKT pointing mortar 25 kg (~4 kg/m2); pointing labour in slips_flat
6.5 | Base starter track + stop trims | 44.3 | m | 6 | 3.4 |  |  |  | MKT base starter track / stop trims
Bill total

## Bill 7
DG-T03 Type 03 - Brick two-storey single - Bill 7 - Opening schedule (doors + windows)
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
7.1 | L1-D01 Electric insulated roller garage door 2,400 x 2,286 S.O., RAL 7016: 77 slats, box behind the lintel course, guides, tubular motor, 2 remotes, manual override, brush seals | 1 | nr | 1658.37 | 204 |  |  |  | MKT electric insulated roller door 2.4 x 2.3, Yorkshire supply; accessories GBP 8.37 incl.
7.2 | L1-D02 Composite personnel door 900 x 2,286 S.O.: frame, fixed overpanel, multipoint lock, lever handles, low threshold; illbruck ME110 internal membrane (5.5 m) + sealant | 1 | nr | 1067.94 | 184.96 |  |  |  | NGR single door (composite + overpanel); accessories GBP 17.94 incl.
7.3 | L1-W01 Alu-clad timber window 1,200 x 914 S.O., RAL 7016, DGU, trickle vent, handles, aluminium cill; illbruck ME110 internal membrane (4.2 m) + sealant | 1 | nr | 753.29 | 113.56 |  |  |  | NGR 280 per window + 420/m2 (base on the window line); accessories GBP 12.43 incl.
7.4 | L1-W11 Alu-clad timber window 600 x 914 S.O., RAL 7016, DGU, trickle vent, handles, aluminium cill; illbruck ME110 internal membrane (3.0 m) + sealant | 1 | nr | 519.65 | 110.16 |  |  |  | NGR 280 per window + 420/m2 (base on the window line); accessories GBP 9.22 incl.
7.5 | L1-W12 Alu-clad timber window 600 x 914 S.O., RAL 7016, DGU, trickle vent, handles, aluminium cill; illbruck ME110 internal membrane (3.0 m) + sealant | 1 | nr | 519.65 | 110.16 |  |  |  | NGR 280 per window + 420/m2 (base on the window line); accessories GBP 9.22 incl.
7.6 | L1-W13 Alu-clad timber window 900 x 914 S.O., RAL 7016, DGU, trickle vent, handles, aluminium cill; illbruck ME110 internal membrane (3.6 m) + sealant | 1 | nr | 636.46 | 111.86 |  |  |  | NGR 280 per window + 420/m2 (base on the window line); accessories GBP 10.82 incl.
Bill total

## Bill 8
DG-T03 Type 03 - Brick two-storey single - Bill 8 - Electrical installation
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
8.1 | 2 double sockets + 2 LED battens, sub-board, short feed, test + cert | 1 | item | 520 | 476 |  |  |  | TLS / MKT 2 double sockets, 2 LED battens, sub-board, short feed, test + cert
Bill total

## Bill 9
DG-T03 Type 03 - Brick two-storey single - Bill 9 - Design + approvals (provisional)
Ref | Item | Qty | Unit | Supply rate | Install rate | Supply | Install | Total | Source / note
9.1 | Building control (provisional) | 1 | item | 650 | 0 |  |  |  | Building control (LABC) - provisional
9.2 | Structural engineer - calcs + details (provisional) | 1 | item | 850 | 0 |  |  |  | Structural engineer calcs - provisional
9.3 | Drawings / lawful development certificate (provisional) | 1 | item | 1250 | 0 |  |  |  | Drawings / PD certificate / planning - provisional
Bill total